## Task_Table
ID | Active | Task Mode | Name | Duration | Start | Finish | Predecessors | Outline Level | Notes
0 | Yes | Auto Scheduled |  | 22 days | September 15, 2025 8:00 AM | October 14, 2025 5:00 PM |  | 0
1 | Yes | Auto Scheduled | Planning Plase | 11 days | September 15, 2025 8:00 AM | September 29, 2025 5:00 PM |  | 1
2 | Yes | Auto Scheduled | Assign launch team members | 1 day | September 15, 2025 8:00 AM | September 15, 2025 5:00 PM |  | 2
3 | Yes | Auto Scheduled | Design and order marketing material | 2 wks | September 16, 2025 8:00 AM | September 29, 2025 5:00 PM | 2 | 2
4 | Yes | Auto Scheduled | Planning complete! | 0 days | September 29, 2025 5:00 PM | September 29, 2025 5:00 PM | 3 | 2
5 | Yes | Auto Scheduled | Public Launch Phase | 10 days | September 30, 2025 8:00 AM | October 13, 2025 5:00 PM | 1 | 1
6 | Yes | Auto Scheduled | Distribute advance copies | 2 days | September 30, 2025 8:00 AM | October 1, 2025 5:00 PM |  | 2 | Get recipient list from publicist.
7 | Yes | Auto Scheduled | Coordinate magazine feature articles | 7 days | October 2, 2025 8:00 AM | October 10, 2025 5:00 PM | 6 | 2
8 | Yes | Auto Scheduled | Launch social media programs for book | 1 day | October 13, 2025 8:00 AM | October 13, 2025 5:00 PM | 7 | 2
9 | Yes | Auto Scheduled | Launch social media programs for book | 1 day | October 14, 2025 8:00 AM | October 14, 2025 5:00 PM | 8 | 1

## Resource_Table
ID | Name | Initials | Type | Material Label | Group | Email Address | User Logon Account | Max Units | Standard Rate | Cost Per Use | Notes
0 |  |  | Work |  |  |  |  | 100% | $0.00/h | 0

## Assignment_Table
Task Name | Resource Name | % Work Complete | Work | Units