## Task_Table
ID | Active | Task Mode | Name | Duration | Start | Finish | Predecessors | Outline Level | Notes
1 | Yes | Auto Scheduled | Dự án thiết kế | 10 days | September 22, 2025 8:00 AM | October 3, 2025 5:00 PM |  | 1
2 | Yes | Auto Scheduled | Thiết kế hệ thống | 10 days | September 22, 2025 8:00 AM | October 3, 2025 5:00 PM |  | 2
3 | Yes | Auto Scheduled | Thiết kế giao diện | 10 days | September 22, 2025 8:00 AM | October 3, 2025 5:00 PM |  | 3
4 | Yes | Auto Scheduled | Thiết kế cơ sở dữ liệu | 10 days | September 22, 2025 8:00 AM | October 3, 2025 5:00 PM |  | 3

## Resource_Table
ID | Name | Initials | Type | Material Label | Group | Email Address | User Logon Account | Max Units | Standard Rate | Cost Per Use | Notes
1 | Nguyễn Hoàng Minh | N | Work |  |  |  |  | 100% | $12.00/h | 0
2 | Phạm Thái Ngân | P | Work |  |  |  |  | 100% | $8.00/h | 0

## Assignment_Table
Task Name | Resource Name | % Work Complete | Work | Units
Thiết kế giao diện | Nguyễn Hoàng Minh | 0.5 | 80h | 100%
Thiết kế cơ sở dữ liệu | Phạm Thái Ngân | 0.5 | 80h | 100%